## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
NatRisk Quality Assurance and Monitoring
Work Package 5
Sally Priest/Mike Dawney
Middlesex University
Kickoff Meeting/ 16th Dec 2016
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2: General Principles
Light touch critical self-assessment by WP leaders (bi-annual) and Partner contact persons (annual)
Overall quality measures
  Achievement of targets on time (ref LFM)
  Active participation
  Appropriate expenditure and financial reporting
External quality review at project mid-point and in final year.
Ongoing monitoring with PMC to alert on and resolve issues
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 3: Quality Assurance Committee
QAC is responsible for quality oversight of the project, reporting to PMC
QAC is chaired by Middlesex University
Membership to be determined at the Kickoff meeting (BOKU, OE, UNI,MU)
QAC will review self-assessments and report to PMC after bi-annual QAC meetings
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 4: Primary Responsibilities
Quality Control Plan
  The Quality Control plan will be developed and approved by SC by January 2017.
Monitoring
  preventative function focuses on the review of the objectives, priorities, methodology and planned activities
  advisory function focuses on suggestion to follow the project implementation and solve issues
  control function focuses on assessment of the results, impact, sustainability and visibility
Quality assessment of activities
Interproject coaching (with PMC)
Liaison with National Agencies (with PMC)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 5: Initial Tasks
  Establishment of QAC working methods
  Development of quality control plan
  Preparation of self-assessment forms
  Establishment of work schedule
  Development of “robust, specific quality indicators”
Development of master curricula for natural disasters risk management in Western Balkan countries