## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
Overview of the first project year
Milan Gocić
University of Niš
Kick-off meeting/ 16th December 2016
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2: Workplan for project year 1
Development of master curricula for natural disasters risk management in Western Balkan countries
Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 | Identification of natural disasters to be managed in WB | 18 | 3X= | 3X | 3X | 3X | 3X= | 3X= |  |  |  |  |  | 
1.2 | Introduction with established practices in EU countries for NDRM | 18 | 3X= | 3X | 3X | 3X | 3X= | 3X= |  |  |  |  |  | 
1.3 | Workshop on master curricula best practices in EU countries | 11 |  |  |  |  | 3= | 4= | 4X= |  |  |  |  | 
2.1 | Development of aims, specific competencies and learning competencies of master curricula in WB HEIs | 11 |  |  |  |  |  | 2X | 2X | 2X | 2X | 3X |  | 
2.2 | Development of courses content and syllabi | 26 |  |  |  |  |  | 3X | 3X | 4X | 4X | 4X | 4X | 4X
2.3 | Training of teaching staff for innovative teaching methods | 9 |  |  |  |  |  |  | = | 2= | 2= | = | = | 2=
2.4 | Providing of students’ internships positions | 1 |  |  |  |  |  |  |  |  | X | X | X | X
2.5 | Harmonization of teaching environment with EU best practices and purchasing of laboratory equipment and literature | 11 |  | 2X | 2X | X | X | X | 2X | 2X |  |  |  | 
3.1 | Surveillance of citizens’ and public sector awareness regarding natural disasters | 16 |  | 2X | 3X | 3X | 4X | 4X |  |  |  |  |  | 
3.2 | Study visits and analysis of courses best practices in EU countries | 9 |  |  |  |  |  |  | = | 2= | 2= | = | = | 2=
3.3 | Development of trainings’ content corresponding educational materials and selection of teaching staff | 9 |  |  |  |  |  |  |  |  |  | 3X= | 3X | 3X
4.1 | Defining of admission requirements and enrolment of students | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.2 | Implementation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.3 | Implementation of students’ internships | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.4 | Implementation of trainings for citizens and public sector | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.5 | Self-evaluation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.6 | Self-evaluation of trainings for citizens and public sector | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.1 | Regular Quality Assurance Committee meetings | 5 |  |  |  |  |  | 2X= |  |  |  |  |  | 3X=
5.2 | Development of the quality control plan | 6 | 2X= | 2X= | 2X= |  |  |  |  |  |  |  |  | 
5.3 | Conduct external review of the project | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.4 | External financial control | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.5 | Inter-project coaching | 0 |  |  |  |  |  |  |  |  |  |  |  | 
6.1 | Creation of the dissemination plan for the project | 6 |  |  | 2X= | 2X= | 2X= |  |  |  |  |  |  | 
6.2 | Development and maintenance of project website and creation of promotional materials and campaigns | 10 |  | 2X | 2X= | X= | X= | X= | X | X | X | X | X | X
6.3 | Promotional activity for student enrolment | 0 |  |  |  |  |  |  |  |  |  |  |  | 
6.4 | Promotional activity for trainings | 2 |  |  |  |  |  |  |  |  |  |  | X | X
7.1 | Creation of sustainability plan | 6 |  | 2X= | 2X= | 2X= |  |  |  |  |  |  |  | 
7.2 | Accreditation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
7.3 | Realization of student and staff mobilities between WB and EU partners | 0 |  |  |  |  |  |  |  |  |  |  |  | 
8.1 | Kick-off meeting | 2 | 3X= |  |  |  |  |  |  |  |  |  |  | 
8.2 | Regular Steering Committee and Project Management meetings | 5 |  |  |  |  |  | 2X= |  |  |  |  |  | 3X=
8.3 | Development of guidelines on the project management and reporting | 6 |  |  | 2X= | 2X= | 2X= |  |  |  |  |  |  | 
8.4 | Day-to-day coordination of project activities | 15 | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X=
8.5 | Submission of interim and final reports | 0 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 3: WP1 – to do list Analysis of natural disasters needed to be managed in Western Balkan region
Development of master curricula for natural disasters risk management in Western Balkan countries
1.1 Identification of natural disasters to be managed in WB | 
Report on natural disasters in WB – BOKU in consultation with contact persons from all WBC institutions | 14.03.2017
1.2 Introduction with established practices in EU countries for NDRM | 
Survey of established practices in EU countries for NDRM – BOKU in consultation with EU partners institutions | 14.03.2017
1.3 Workshop on master curricula best practices in EU countries | 
Report on master curricula best practices in EU partners and Catalogue of competencies - BOKU in consultation with contact persons from all institutions (Workshop in Vienna, 4-8 April) | 14.05.2017

## Slide 4: WP2 – to do list Development of master curricula
Development of master curricula for natural disasters risk management in Western Balkan countries
2.1 Development of aims, specific competencies and learning competencies of master curricula in WB HEIs | 
Defined aims, specific competencies and learning outcomes of master curriculum per HEI in WB; Catalogue of courses – All WBC institutions | 14.08.2017
2.2 Development of courses content and syllabi | 
Defined courses content and syllabi – All WBC institutions | 14.12.2017
2.3 Training of teaching staff for innovative teaching methods | 
Teaching staff trained – EU partners in a colaboration with WBC institutions Note: 1) May 2017 - OE (19 staff): UNI - 6, KPA - 3, UPKM - 3, VSUP - 2, TCASU - 2, UNID – 3 2) June 2017 - MUHEC (14 staff): UNI - 6, UPKM - 3, UNSA - 3, TCASU – 2 3) July 2017 - TUC (20 staff): UNI - 6, KPA - 3, UPKM - 3, UNSA - 3, VSUP - 2, UNID – 3 4) September 2017 – UNIME (19 staff): UNI - 6, UPKM - 3, UNSA - 3, VSUP - 2, TCASU - 2, UNID – 3 5) November 2017 - BOKU (12 staff): UNI - 6, KPA - 3, UNSA - 3 | 14.12.2017

## Slide 5: WP2 – to do list Development of master curricula
Development of master curricula for natural disasters risk management in Western Balkan countries
2.4 Providing of students’ internships positions | 
Agreements for internships signed - All WBC institutions (Only to start collaboration with public sector) | 14.10.2019
2.5 Harmonization of teaching environment with EU best practices and purchasing of laboratory equipment and literature | 
Laboratories equipped – All WBC institutions | 14.06.2017

## Slide 6: WP3 – to do list Development of trainings for citizens and public sector
Development of master curricula for natural disasters risk management in Western Balkan countries
3.1 Surveillance of citizens’ and public sector awareness regarding natural disasters | 
Survey of citizens’ and public sector awareness – UNID in consultation with contact persons from all WBC institutions | 14.03.2017
3.2 Study visits and analysis of courses best practices in EU countries | 
Study visit reports – In conjuction with 2.3 | 14.03.2017
3.3 Development of trainings’ content corresponding educational materials and selection of teaching staff | 
Trainings’ materials prepared, teachers selected - UNID in consultation with contact persons from all WBC institutions | 14.02.2018

## Slide 7: WP5 – to do list Quality assurance and monitoring
Development of master curricula for natural disasters risk management in Western Balkan countries
5.1 Regular Quality Assurance Committee meetings | 
Minutes of the meetings – MUHEC in consultation with contact persons from UNI, BOKU, OE (first: BOKU April 2017, second: UNIME September 2017) | 14.10.2019
5.2 Development of the quality control plan | 
Quality control plan adopted – MUHEC in consultation with contact persons from UNI, BOKU, OE | 14.01.2017

## Slide 8: WP6 – to do list Dissemination
Development of master curricula for natural disasters risk management in Western Balkan countries
6.1 Creation of the dissemination plan for the project | 
Dissemination plan created – UNI in consultation with contact persons from all institutions | 14.03.2017
6.2 Development and maintenance of project website and creation of promotional materials and campaigns | 
Promotion material created – All WBC institutions | 14.10.2019
6.4 Promotional activity for trainings | 
Trainings promoted - All WBC institutions | 14.10.2019

## Slide 9: WP7 – to do list Exploitation
Development of master curricula for natural disasters risk management in Western Balkan countries
7.1 Creation of sustainability plan | 
Sustainability plan created - UNI in consultation with contact persons from all institutions | 14.03.2017

## Slide 10: WP8 – to do list Project management
Development of master curricula for natural disasters risk management in Western Balkan countries
8.1 Kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions | 14.11.2016
8.2 Regular Steering Committee and Project Management meetings | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions (first: BOKU April 2017, second: UNIME September 2017) | 14.10.2019
8.3 Development of guidelines on the project management and reporting | 
Guidelines on the project management and reporting created - UNI in consultation with contact persons from all institutions | 14.03.2017
8.4 Day-to-day coordination of project activities | 
Project correspondence - UNI in consultation with contact persons from all institutions | 14.10.2019

## Slide 11: Reports to coordinator
Report from the Kick-off meeting
Reports from the meetings of the SC, PMC, QAC to be done by the host institution (2 per year)
Reports from the study visits and workshop to be done by the host institution (6 reports in total)
Reports from staff training sessions (5 reports in total - each one from the EU trainers)
Activity reports - each partner in the project will sent these on every 3 months during the project implementation.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 12: Reports to coordinator
Development of master curricula for natural disasters risk management in Western Balkan countries
Partner’s Financial Report delivered to coordinator | 1st report – 14.04.2017
 | 2nd report – 14.10.2017
Partner’s Technical report on the implementation of the project delivered to coordinator | 1st report – 14.04.2017
 | 2nd report – 14.10.2017

## Slide 13: First year objectives
Kick-off meeting organised
2 meetings of SC, QAC, PMC (months 6 and 12) organised and reports written
Report on natural disasters in WB countries
Survey of established practices in EU countries for NDRM
1 workshop organised and related report written
5 study visits and trainings organised and related reports written
Report on master curricula best practices in EU partners
Analyses on needs, constrains and possibilities for curricula development concluded and related reports written
Catalogue of competencies
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 14: First year objectives
Programme content and methodologies developed and related reports written
Quality assurance plan developed and written
Sustainability plan developed and written
Guidelines on the project management and reporting developed and written
Visual identity created: project logo, project web site, project platform
Several promotional and informative events organised and/or participated in
Project promoted through media
Links with non-academic sector, enterprise sector and policy stakeholders created
Development of master curricula for natural disasters risk management in Western Balkan countries