## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
NatRisk project
Milan Gocić
University of Niš
NEO Serbia preventive monitoring/ 20th April 2017
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2: Basic Information
Contract number 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
Project acronym NatRisk
Project name Development of master curricula for natural disasters risk management in Western Balkan countries
Project duration 15th October 2016 - 14th October 2019
Programme ERASMUS+ – Call for Proposals EAC/A04/2015
Total cost 1,245,746.00 €
Coordinator University of Niš, Serbia
Univerzitetski trg 2, 18000 Niš, Serbia
Project website www.natrisk.ni.ac.rs
Project e-mail natriskuni@gmail.com
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 3: Natural hazards
Development of master curricula for natural disasters risk management in Western Balkan countries
tornado
thunderstorm
landslide
earthquake
volcanic eruption
heavy snowfall
drought
flood
high wind speed

## Slide 4: Natural hazards
Natural hazards cause directly significant loss of life, set back economic and social development, reductions in crop yields, destruction of homes and other infrastructure and indirectly increased food prices and food insecurity.
We cannot avoid natural hazards, but we can prevent them from becoming disasters.
More than 1.5 billion people have been affected by disasters in various ways and the total economic loss was more than $1.3 trillion (Sendai Framework for Disaster Risk Reduction 2015-2030). Between 2002 and 2014 natural disasters in the EU caused over 80000 deaths and over €100 billion of economic losses.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 5: Motivation
Management of natural disasters became the greatest global challenge and an indispensable requirement for sustainable development and is set as a goal both in Europe 2020 (target 3. climate change) and the 2030 agenda for Sustainable Development United Nations (“Goal 13. Take urgent action to combat climate change and its impacts“).
WB countries should above all develop new or improve the existing education in this field, to raise technical capacity and accomplish creation of more efficient systems for better response when natural disasters occur.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 6: Overall Broader Objective
Education of experts for prevention and management of natural disasters in the region of Western Balkan (WB) according to the national and EU policies.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 7: Specific Objectives
Identification of natural disasters to be managed in WB region and all aspects of prevention and consequences in order to define specific competencies for professional practice
Development and implementation of the new advanced master curricula in Natural Disasters Risk Management (NDRM) in line with the Bologna requirements and national accreditation standards
Development of trainings for the public sector and citizens for reaction in case of various natural disasters
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 8: Project Realisation
Identification and analysis of WB problems and needs in NDRM, comparison of best practices in EU and WB, determination of discrepancy level of NDRM in EU and WB (by May 2017).
Development of master curricula with all necessary elements in line with the Europe 2020 strategy, ET 2020, Standards and Guidelines for Quality Assurance in the European Higher Education Area and the Bologna requirements, training of teaching staff (by December 2017), upgrading teaching environment (by June 2017).
Development of educational trainings for citizens and public sector (by February 2018).
Implementation of master curricula with students’ internships and student and staff mobilities (since May 2018) and trainings (since December 2017).
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 9: Student Involment
Students will be informed about developed new master curricula and provided internships in WB and EU partner countries and they will be given opportunity to study in EU within the Special Mobility Strand (45 mobilities).
Students feedback through the self-evaluation of master curricula will be one of the main indicators of the project quality.
Students will be actively involved in promotion of developed master curricula.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 10: Short Term Impact Indicators
Development of master curricula for natural disasters risk management in Western Balkan countries
Short term impact | Target groups/potential beneficiaries | Quantitative indicators | Qualitative indicators
Professional development | Teaching staff | 93 trained staff | Professional performance, assessment, self-evaluation
Innovative knowledge gaining | Students | At least 120 of enrolled and graduated students | Knowledge assessment
Capacity building | Institution | 7 laboratories with new equipment; upgraded 7 libraries with new library units | Better working conditions
Awareness about new educational trainings and their significance | Citizens/public sector | At least 420 registered participants | Interest in trainings participation
Improved competences through educational trainings | Citizens/public sector | At least 420 trained participants; 14 one-day trainings | Knowledge assessment
Innovative skill and knowledge gaining | Students/Staff | At least 15/21 of realized mobilities | Skill and knowledge improvement

## Slide 11: Long Term Impact Indicators
Development of master curricula for natural disasters risk management in Western Balkan countries
Long term impact | Target groups/potential beneficiaries | Quantitative indicators | Qualitative indicators
Quality of teaching staff | Scientific community | Number of scientific papers in international journals in the field of management of natural disasters | Quality of papers
Permanent modernisation and update of master curricula | Experts in management of natural disasters in WB region | Number of newly topics and courses | Periodical reaccreditation
Graduated students with the knowledge that can be immediately implemented in practice | Labour market in WB region | Number of new employees | Quality of measures in improving system for risk reduction
Innovative knowledge application | Wider community | Number of projects related to management of natural disasters by educated proffesionals | Quality of application achieved through the practice

## Slide 12: Sustainability
Seven new master programmes in NDRM at the WB partner HEIs that will be developed, accredited and implemented.
Three new training programmes in NDRM (one per each WB partner country) with training materials for public sector and citizens developed and conducted.
Retrained teaching staff with up-to-date knowledge in NDRM to teach on the new master programmes.
Advanced teaching and learning process introduced.
Introduced new laboratory equipment, library units and software necessary for the continuation of the new master programmes.
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 13: Consortium
EU partners
University of Natural Resources and Life Sciences, Vienna (BOKU, AUSTRIA)
Middlesex University Higher Education Corporation (MUHEC, UK)
University of Messina (UNIME, ITALY)
Óbuda University (OE, HUNGARY)
Technical University of Crete, Chania (TUC, GREECE)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 14: Consortium
Western Balkan partners
University of Niš (UNI, Serbia)
Academy of Criminalistics and Police Studies (KPA, Serbia)
University of Pristina in Kosovska Mitrovica (UPKM, Kosovo*)
University of Sarajevo (UNSA, Bosnia and Herzegovina)
Republic of Srpska - Ministry of Interior, Police College, Department for police education (VSUP, Bosnia and Herzegovina)
Technical College of Applied Sciences Urosevac with temporary seat in Leposavic (TCASU, Kosovo*)
University of Defence in Belgrade (UNID, Serbia)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 15: Consortium
Associated partner
Republic Hydrometeorological Service of Serbia
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 16
NatRisk Map
Development of master curricula for natural disasters risk management in Western Balkan countries
Source: http://ec.europa.eu/programmes/erasmus-plus/projects/eplus-project-details-page/?nodeRef=workspace://SpacesStore/c3a0d5cf-9f44-40b1-8731-23c187fc13ee

## Slide 17: Work Packages
Preparation WP1: Analysis of natural disasters needed to be managed in Western Balkan region
Leader: University of Natural Resources and Life Sciences, Vienna
Preparation WP2: Development of master curricula
Leader: University of Messina
Preparation WP3: Development of trainings for citizens and public sector
Leader: University of Defence in Belgrade
Development WP4: Implementation of developed master curricula and trainings
Leader: University of Sarajevo
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 18: Work Packages
Quality Plan WP5: Quality assurance and monitoring
Leader: Middlesex University Higher Education Corporation
Dissemination & Exploitation WP6: Dissemination
Leader: University of Niš
Dissemination & Exploitation WP7: Exploitation
Leader: University of Niš
Management WP8: Project management
Leader: University of Niš
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 19: Workplan for project year 1
Development of master curricula for natural disasters risk management in Western Balkan countries
Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Ref.nr/ Sub-ref nr | Title |  |  |  |  |  |  |  |  |  |  |  |  | 
1.1 | Identification of natural disasters to be managed in WB | 18 | 3X= | 3X | 3X | 3X | 3X= | 3X= |  |  |  |  |  | 
1.2 | Introduction with established practices in EU countries for NDRM | 18 | 3X= | 3X | 3X | 3X | 3X= | 3X= |  |  |  |  |  | 
1.3 | Workshop on master curricula best practices in EU countries | 11 |  |  |  |  | 3= | 4= | 4X= |  |  |  |  | 
2.1 | Development of aims, specific competencies and learning competencies of master curricula in WB HEIs | 11 |  |  |  |  |  | 2X | 2X | 2X | 2X | 3X |  | 
2.2 | Development of courses content and syllabi | 26 |  |  |  |  |  | 3X | 3X | 4X | 4X | 4X | 4X | 4X
2.3 | Training of teaching staff for innovative teaching methods | 9 |  |  |  |  |  |  | = | 2= | 2= | = | = | 2=
2.4 | Providing of students’ internships positions | 1 |  |  |  |  |  |  |  |  | X | X | X | X
2.5 | Harmonization of teaching environment with EU best practices and purchasing of laboratory equipment and literature | 11 |  | 2X | 2X | X | X | X | 2X | 2X |  |  |  | 
3.1 | Surveillance of citizens’ and public sector awareness regarding natural disasters | 16 |  | 2X | 3X | 3X | 4X | 4X |  |  |  |  |  | 
3.2 | Study visits and analysis of courses best practices in EU countries | 9 |  |  |  |  |  |  | = | 2= | 2= | = | = | 2=
3.3 | Development of trainings’ content corresponding educational materials and selection of teaching staff | 9 |  |  |  |  |  |  |  |  |  | 3X= | 3X | 3X
4.1 | Defining of admission requirements and enrolment of students | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.2 | Implementation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.3 | Implementation of students’ internships | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.4 | Implementation of trainings for citizens and public sector | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.5 | Self-evaluation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
4.6 | Self-evaluation of trainings for citizens and public sector | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.1 | Regular Quality Assurance Committee meetings | 5 |  |  |  |  |  | 2X= |  |  |  |  |  | 3X=
5.2 | Development of the quality control plan | 6 | 2X= | 2X= | 2X= |  |  |  |  |  |  |  |  | 
5.3 | Conduct external review of the project | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.4 | External financial control | 0 |  |  |  |  |  |  |  |  |  |  |  | 
5.5 | Inter-project coaching | 0 |  |  |  |  |  |  |  |  |  |  |  | 
6.1 | Creation of the dissemination plan for the project | 6 |  |  | 2X= | 2X= | 2X= |  |  |  |  |  |  | 
6.2 | Development and maintenance of project website and creation of promotional materials and campaigns | 10 |  | 2X | 2X= | X= | X= | X= | X | X | X | X | X | X
6.3 | Promotional activity for student enrolment | 0 |  |  |  |  |  |  |  |  |  |  |  | 
6.4 | Promotional activity for trainings | 2 |  |  |  |  |  |  |  |  |  |  | X | X
7.1 | Creation of sustainability plan | 6 |  | 2X= | 2X= | 2X= |  |  |  |  |  |  |  | 
7.2 | Accreditation of master curricula | 0 |  |  |  |  |  |  |  |  |  |  |  | 
7.3 | Realization of student and staff mobilities between WB and EU partners | 0 |  |  |  |  |  |  |  |  |  |  |  | 
8.1 | Kick-off meeting | 2 | 3X= |  |  |  |  |  |  |  |  |  |  | 
8.2 | Regular Steering Committee and Project Management meetings | 5 |  |  |  |  |  | 2X= |  |  |  |  |  | 3X=
8.3 | Development of guidelines on the project management and reporting | 6 |  |  | 2X= | 2X= | 2X= |  |  |  |  |  |  | 
8.4 | Day-to-day coordination of project activities | 15 | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X= | 2X=
8.5 | Submission of interim and final reports | 0 |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 20
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 21: NatRisk Management structure
Project Consortium (12 partners) ↔ Contact Persons
Coordinator Institution UNI ↔ Project Coordinator
Steering Committee (SC): one representative from each partner institution, 12
Project Management Committee (PMC): Project Coordinator + 8 WP Coordinators
Work Package Leaders: representatives from UNI, BOKU, MUHEC, UNSA, UNIME, UNID
Quality Assurance Committee: 4 members (UNI, BOKU, MUHEC, OE)
Mobility Strand Team: 5 members (UNI)
Task Leaders: from each institution involved in a particular WP
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 22: Steering Committee
Development of master curricula for natural disasters risk management in Western Balkan countries
No. | Acronym | Name
1 | UNI | Dragan Antić
2 | BOKU | Michael Tritthart
3 | MUHEC | Sally Priest
4 | KPA | Saša Mijalković
5 | UPKM | Nebojša Arsić
6 | UNSA | Emina Hadžić
7 | VSUP | Mile Šikman
8 | TCASU | Predrag Stanojević
9 | UNIME | Giuseppe Tito Aronica
10 | OE | Agota Dregelyi-Kiss
11 | UNID | Boban Đorović
12 | TUC | Georgios Stavroulakis

## Slide 23: Project Management Committee
Development of master curricula for natural disasters risk management in Western Balkan countries
No. | Acronym | Name
1 | UNI | Milan Gocić, Project Coordinator
2 | BOKU | Michael Tritthart, WP1 Leader
3 | UNIME | Giuseppe Tito Aronica, WP2 Leader
4 | UNID | Miroslav Talijan, WP3 Leader
5 | UNSA | Emina Hadžić, WP4 Leader
6 | MUHEC | Sally Priest, WP5 Leader
7 | UNI | Dejan Rančić, WP6 Leader
8 | UNI | Slaviša Trajković, WP7 Leader

## Slide 24: Quality Assurance Committee
Development of master curricula for natural disasters risk management in Western Balkan countries
No. | Acronym | Name
1 | UNI | Zoran Nikolić
2 | BOKU | Kurt Glock
3 | MUHEC | Sally Priest
4 | OE | Gabriella Farkas

## Slide 25: Mobility Strand Team
Development of master curricula for natural disasters risk management in Western Balkan countries
No. | Acronym | Name
1 | UNI | Ivica Manić
2 | UNI | Milan Gocić
3 | UNI | Vesna Stankov-Jovanović
4 | UNI | Slaviša Trajković
5 | UNI | Mionir Raos