|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **No** | **FROM** | **TO** | **Staff** | **Duration (days)** | **Period** |
| 1 | UNI | BOKU | 2 | 7 | completed |
| 2 | 15 | completed |
| 1 | 30 | Completed |
|  |  | 1 | 30 |  |
| BOKU | UNI | 2 | 7 | Completed |
| 2 | UNI | UNIME | 2 | 7 | In progress |
| 2 | 15 | In progressIn progress |
| 2 | 30 | In progress |
| UNIME | UNI | 3 | 7 | May, 2019 |
| 3 | UNI | OE | 2 | 7 | Till July, 2019, Call will be announced in the end of September 2018 |
| 2 | 15 |
| 2 | 30 |
| OE | UNI |  |  |  |
| 4 | UNI | MUHEC | 2 | 7 | Completed |
| 2 | 15 | Completed |
| 2 | 30 | Completed |
| MUHEC | UNI | 2 | 7 | To be confirmed |
| 5 | UNI | UNSA | 2 | 7 | Till July, 2019, Call will be announced in the end of September 2018 |
| 2 | 15 |
| 2 | 30 |
| UNSA | UNI | 3 | 7 |  |
| 6 | UNI | TUC | 2 | 7 | Completed |
| 2 | 15 | Completed |
| 2 | 30 | Completed |
| TUC | UNI | 3 | 7 |  |
| 7 | UNSA | BOKU | 3 | 7 | Call will be announced till the end of September |
| 2 | 15 |  |
| BOKU | UNSA | 2 | 7 | Call is announced, candidates selected, in progress |
| 8 | UNSA | UNIME | 3 | 7 | September 2018 |
| 2 | 15 |  |
| UNIME | UNSA | 3 | 7 | May 2019 |
| 9 | MUHEC | UNSA | 2 | 7 | To be confirmed |
| 10 | TUC | UNSA | 3 | 7 |  |
| 11 | KPA | OE | 4 | 7 | November 2018 |
| OE | KPA | 4 | 7 | October 2018 |
| 12 | KPA | UBL |  |  |  |
| UBL | KPA  | 3 | 7 |  |
| 13 | KPA | TUC | 3 | 7 | In progress |
| 14 | KPA | MUHEC | 3 | 7 | October 2018 |
| 15 | UPKM | UNSA | 3 | 7 | To be confirmed |
| 16 | UPKM | OE | 3/4 | 7 | Completed, one in progress |
| 18 | MUHEC | UPKM | 2 | 7 | To be confirmed |
| 19 | UPKM | UBL | 3 | 7 | To be confirmed |
| 20 | UBL | OE | 3 | 7 | in progress |
| 21 | TCASU | UBL | 3 | 7 | To be confirmed |
| 22 | TCASU | KPA | 3 | 7 | To be confirmed |
| 23 | TCASU | TUC | 3 | 7 | Completed |
| 24 | UNID | OE | 3 | 7 | To be confirmed, November 2018 |
| 25 | UNID | MUHEC | 3 | 7 | need confirmation of preferred week between 19/11/18 and 16/12/18. |
| 26 | UNID | UNIME | 3 | 7 | To be confirmed |

|  |
| --- |
| **Staff**  |
| 119 |

|  |  |
| --- | --- |
| Staff from Partner Countries | 93 |
| Staff from Programme Countries | 26 |