## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
Financial plan and its realization
Milan Gocić
University of Niš
Fifth Steering Committee meeting/ 20th March 2019
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2: NatRisk budget info
The grant shall be of a maximum of EUR 1,245,746.00 and shall take the form of:
Staff costs: 350,638 EUR
Travel costs: 78,980 EUR
Costs of stay 182,715 EUR
Equipment costs: 264,800 EUR
Subcontracting: 48,000 EUR
Special Mobility Strand: 320,613 EUR
Total project expenditures: 1,245,746 EUR
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 3: Second installment from EACEA to the Project coordinator
  First installment: 622,873.00 EUR (SMS 160,306.50 EUR + 462,566.50 EUR)
  Second installment: 496,298.40 EUR (SMS 128,245.20 EUR + 368,053.20 EUR)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 4: Financial report
Development of master curricula for natural disasters risk management in Western Balkan countries
Code | Partner name | Acronym | 12-Mar-19
P1 | University of Nis | UNI | 187,917.40
P2 | University of Natural Resources and Life Sciences, Vienna | BOKU | 41,587.00
P3 | Middlesex University | MUHEC | 30,632.00
P4 | Academy of Criminalistics and Police Studies | KPA | 72,101.56
P5 | University of Pristina in Kosovska Mitrovica | UPKM | 69,652.97
P6 | University of Sarajevo | UNSA | 59,741.96
P7 | University of Banja Luka | UBL | 40,417.09
P8 | Technical College of Applied Sciences Urosevac with temporary seat in Leposavic | TCASU | 44,420.70
P9 | University of Messina | UNIME | 32,138.00
P10 | Óbuda University | OE | 19,502.00
P11 | University of Defence in Belgrade | UNID | 59,488.44
P12 | Technical University of Crete, Chania, Greece | TUC | 21,421.00
 | Total in percentage: 73.40% |  | 679,020.12
Total: 925,133.00

## Slide 5: Special Mobility Strand
Development of master curricula for natural disasters risk management in Western Balkan countries
Code | Acronym | Total | Spent | Teacher realized | Student realized
P1 | UNI | 123,456.00 | 78,542.00 | 34/36 | 0/12
P2 | BOKU | 11,880.00 | 2,790.00 | 2/4 | 0/4
P3 | MUHEC | 11,520.00 |  | 0/6 | 0/2
P4 | KPA | 32,240.00 | 7,705.00 | 7/10 | 0/5
P5 | UPKM | 22,090.00 | 3,765.00 | 3/10 | 0/7
P6 | UNSA | 42,337.00 |  | 0/13 | 0/7
P7 | UBL | 15,660.00 |  | 0/6 | 0/3
P8 | TCASU | 9,330.00 | 6,690.00 | 6/9 | 0/0
P9 | UNIME | 22,470.00 |  | 0/6 | 0/4
P10 | OE | 8,255.00 | 5,200.00 | 4/4 | 0/2
P11 | UNID | 11,430.00 | 7,245.00 | 6/9 | 0/0
P12 | TUC | 9,945.00 |  | 0/6 | 0/1
 |  | 320,613.00 | 113,697.00 | 64/119 | 0/47
Difference:
206,916.00 EUR
Total in percentage: 35.46%

## Slide 6: Financial report
Development of master curricula for natural disasters risk management in Western Balkan countries
Code | Acronym | 12-Mar-19 | SMS | Total | Instalment | Not transferred
P1 | UNI | 187,917.40 | 78,542.00 | 266,459.40 | 328,076.10 | 
P2 | BOKU | 41,587.00 | 2,790.00 | 44,377.00 | 53,162.40 | 6,645.30
P3 | MUHEC | 30,632.00 |  | 30,632.00 | 41,356.70 | 11,816.20
P4 | KPA | 72,101.56 | 7,705.00 | 79,806.56 | 95,996.80 | 11,999.60
P5 | UPKM | 69,652.97 | 3,765.00 | 73,417.97 | 88,242.96 | 11,124.80
P6 | UNSA | 59,741.96 |  | 59,741.96 | 92,813.20 | 26,518.20
P7 | UBL | 40,417.09 |  | 40,417.09 | 56,322.04 | 16,193.80
P8 | TCASU | 44,420.70 | 6,690.00 | 51,110.70 | 59,148.60 | 0.00
P9 | UNIME | 32,138.00 |  | 32,138.00 | 45,593.80 | 13,026.80
P10 | OE | 19,502.00 | 5,200.00 | 24,702.00 | 27,548.80 | 3,443.60
P11 | UNID | 59,488.44 | 7,245.00 | 66,733.44 | 68,689.25 | 20,862.80
P12 | TUC | 21,421.00 |  | 21,421.00 | 28,368.20 | 8,105.20
 |  | 679,020.12 | 113,697.00 | 792,717.12 | 985,319.35 | 135,852.35
Difference:
453,028.88 EUR
Total:
1,245,746.00 EUR

## Slide 7: WP7.3 Realization of mobilities – training weeks
Staff: 3 UNI to MUHEC (0), 3 UNI to UNIME (0), 3 KPU to OE (3), 3 UPKM to TUC (3), 3 UNSA to UNIME (0), 2 UBL to OE (0), 2 TCASU to TUC (2), 2 UNID to UNIME (2) = 21 (10) x 7 days (5 + 2 for travelling) – 120 EUR per day + travelling (ITR, agenda, certificate of attendance, and financial documentation)
Students: 1 UNI to MUHEC (0), 1 UNI to UNIME (0), 2 KPU to OE (0), 1 UPKM to TUC (0), 1 UNSA to UNIME (0), 1 UBL to OE (0), 1 TCASU to TUC (0), = 8 (0) x 14 days (12 + 2 for travelling) – 55 EUR per day + travelling (ITR, agenda, certificate of attendance, and financial documentation)
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 8: How to spend the rest of NatRisk money?
Development of master curricula for natural disasters risk management in Western Balkan countries
453,028.88 EUR

## Slide 9: 10 % of HEI’s financing
Development of master curricula for natural disasters risk management in Western Balkan countries