## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
Fourth Risk monitoring document
Milan Gocić
University of Niš
Fifth Steering Committee meeting/ 20th March 2019
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2
Development of master curricula for natural disasters risk management in Western Balkan countries
Risk title | Accreditation of master curricula in WB countries | 
Description of risk | Probability high Impact high | Master curricula in WB countries should be accredited in line with the national legislation in WB countries on time .
Preventive action | WB partner HEIs should prepare and submit necessary documentation on time i.e. till the end of March 2018. | 
Corrective action | WB HEIs should prepare and correct accreditation documentation in line with the national legislation to avoid problems | 
Decision of SC, QAC and Project Coordinator | To contact Commission for Accreditation in WB countries and other relevant agencies and institutions. |