**RISK MONITORING FORM[[1]](#footnote-1)**

|  |  |
| --- | --- |
| Project title | Development of master curricula for natural disasters risk management in Western Balkan countries  |
| Project acronym | NatRisk |
| Project reference number | 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP |
| Coordinator | University of Nis |
| Project start date | October 15, 2016 |
| Project duration | 36 months |

Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP

*"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"*

**RISK DESCRIPTION**

|  |  |
| --- | --- |
| **Risk title** | **Accreditation of master curricula in WB countries** |
| **Description of risk** | **Probability**high**Impact**high | Master curricula in WB countries should be accredited in line with the national legislation in WB countries on time. |
| **Preventive action** | *WB partner HEIs should prepare and submit necessary documentation on time i.e. till the end of March 2018.*  |
| **Corrective action** | *WB HEIs should prepare and also correct accreditation documentation in line with the national legislation to avoid problems* |
| **Decision of SC, QAC and Project Coordinator** | *To contact Commission for Accreditation in WB countries and other relevant agencies and institutions.*  |

Location, date Signature

Nis, 15 March 2019 

1. *The Risks monitoring form should be updated after each SC organized.* *Project Coordinator with WP leaders and QAC plans and implements risk responses. This form has to be filled by Project Coordinator and sent on e-mail address:* natriskuni@gmail.com *five days after event.*  [↑](#footnote-ref-1)