## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
First Risk monitoring document
Milan Gocić
University of Niš
Second Steering Committee meeting/ 19th September 2017
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2
Development of master curricula for natural disasters risk management in Western Balkan countries
Risk title | Staff and student mobilities realization in WB countries | 
Description of risk | Probability medium Impact high | „The amount corresponding to the subsistence costs must be paid in full and directly to the concerned student according to the modality established in the student Grant Agreement. In order to ensure that on the one hand participating students receive the full amount foreseen for their subsistence costs and on the other hand participating institutions are not confronted with budgetary losses resulting from variations in the exchange rate from or to euros, consortia are strongly recommended to manage their SMS grants in an account in euros.“ According to national legislation in WB countries, SMS scholarships are in taxation regime.
Preventive action | WB HEIs should address jointly the Ministry of Finance and government explaining discrepancy in scholarship payment between national an EACEA rules | 
Corrective action | WB HEIs should apply national legislation to avoid problems | 
Decision of SC, QAC and Project Coordinator | To approach the Erasmus+ CBHE project Knowledge for Resilient Society 573942-2016 (K-FORCE), and jointly address the Ministry of Finance in order to resolve the issue of taxation of Special Mobility Strand scholarships | 

## Slide 3
Development of master curricula for natural disasters risk management in Western Balkan countries
Risk title | Unfulfilled condition financial plan for second installment | 
Description of risk | Probability high Impact high | Second payment of 40% of the maximum amount if: at least 70% of the previous pre-financing installment is spent the statement of costs incurred and the request for payment is sent to EACEA the progress report on the implementation of the Action (Intermediate report) is sent to EACEA
Preventive action | Suggest partners to respect the planned deadlines for project activities and to prepare financial documentation on time after finished activities or achieved deliverables. | 
Corrective action | Make consultation with the Project Coordinator and legal representatives from own HEI to fulfill the condition for second installment as soon as possible not to cause delaying of project activities. | 
Decision of SC, QAC and Project Coordinator | Contact persons of NatRisk partner HEIs who have problems in realization of financial plan must contact the Project Coordinator and try to solve problems. They must also contact HEI legal representatives to improve preparing financial documentation. WB HEIs must realize project activity that is out of foreseen deadline. |