## Slide 1: Development of master curricula for natural disasters risk management in Western Balkan countries
Financial plan and its realization
Milan Gocić
University of Niš
Sixth Steering Committee meeting/ 05th September 2019
Project number: 573806-EPP-1-2016-1-RS-EPPKA2-CBHE-JP
"This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein"

## Slide 2: Financial report
Development of master curricula for natural disasters risk management in Western Balkan countries
Code | Partner name | Acronym | 23-Aug-19
P1 | University of Nis | UNI | 189,832.40
P2 | University of Natural Resources and Life Sciences, Vienna | BOKU | 49,808.00
P3 | Middlesex University | MUHEC | 37,598.00
P4 | University of Criminal Investigation and Police Studies | KPU | 81,206.56
P5 | University of Pristina in Kosovska Mitrovica | UPKM | 77,120.97
P6 | University of Sarajevo | UNSA | 69,950.96
P7 | University of Banja Luka | UBL | 55,736.88
P8 | Technical College of Applied Sciences Urosevac with temporary seat in Leposavic | TCASU | 56,272.56
P9 | University of Messina | UNIME | 32,893.00
P10 | Óbuda University | OE | 23,847.00
P11 | University of Defence in Belgrade | UNID | 73,281.44
P12 | Technical University of Crete, Chania, Greece | TUC | 25,147.00
 | Total in percentage: 83.67% |  | 774,025.97
Total: 925,133.00

## Slide 3: Special Mobility Strand
Development of master curricula for natural disasters risk management in Western Balkan countries
Code | Acronym | Total | Spent | Staff | Student
P1 | UNI | 123,456.00 | 89,792.00 | 34/36 | 6/12
P2 | BOKU | 11,880.00 | 4,185.00 | 3/7 (4) | 0/1 (1)
P3 | MUHEC | 11,520.00 | 6,975.00 | 5/8 (1) | 0/0
P4 | KPU | 32,240.00 | 11,055.00 | 9/10 | 0/5
P5 | UPKM | 22,090.00 | 9,045.00 | 9/10 | 0/7
P6 | UNSA | 42,337.00 | 10,191.00 | 7/13 (5) | 0/7 (4)
P7 | UBL | 15,660.00 | 6,120.00 | 6/6 | 0/3 (1)
P8 | TCASU | 9,330.00 | 9,330.00 | 9/9 | 0/0
P9 | UNIME | 22,470.00 |  | 0/8 (1) | 0/3
P10 | OE | 8,255.00 | 5,200.00 | 4/5 | 0/1 (1)
P11 | UNID | 11,430.00 | 11,430.00 | 9/9 | 0/0
P12 | TUC | 9,945.00 |  | 0/6 | 0/1
 |  | 320,613.00 | 163,323.00 | 95/125 (11) | 6/41 (7)
Difference:
157,290.00 EUR
Total in percentage: 50.94%

## Slide 4: Financial report
Development of master curricula for natural disasters risk management in Western Balkan countries
Code | Acronym | 23-Aug-19 | SMS | Total | Budget | Percentage | Not transferred
P1 | UNI | 189,832.40 | 89,792.00 | 279,624.40 | 364,529.00 | 76.71 | 
P2 | BOKU | 49,808.00 | 4,185.00 | 53,993.00 | 66,453.00 | 81.25 | 6,645.30
P3 | MUHEC | 37,598.00 | 6,975.00 | 44,573.00 | 59,081.00 | 75.44 | 5,908.10
P4 | KPU | 81,206.56 | 11,055.00 | 92,261.56 | 119,996.00 | 76.89 | 11,999.60
P5 | UPKM | 77,120.97 | 9,045.00 | 86,165.97 | 111,248.00 | 77.45 | 0.00
P6 | UNSA | 69,950.96 | 10,191.00 | 80,141.96 | 132,591.00 | 60.44 | 13,259.10
P7 | UBL | 55,738.88 | 6,120.00 | 61,858.88 | 80,969.00 | 76.40 | 8,096.90
P8 | TCASU | 56,272.56 | 9,330.00 | 65,602.56 | 66,469.00 | 98.70 | 0.00
P9 | UNIME | 32,893.00 |  | 32,893.00 | 65,134.00 | 50.50 | 13,026.80
P10 | OE | 23,847.00 | 5,200.00 | 29,047.00 | 34,436.00 | 84.35 | 0.00
P11 | UNID | 74,612.64 | 11,430.00 | 86,042.64 | 104,314.00 | 82.48 | 0.00
P12 | TUC | 25,147.00 |  | 25,147.00 | 40,526.00 | 62.05 | 8,105.20
 |  | 774,025.97 | 163,323.00 | 937,348.97 | 1,245,746.00 | 75.24 | 67,041.00
Difference:
308,397.03 EUR

## Slide 5: How to spend the rest of NatRisk money?
Development of master curricula for natural disasters risk management in Western Balkan countries
308,397.03 EUR

## Slide 6: P1 - UNI
Staff costs – documentation
WP5.3 External evaluation of the project - documentation
WP5.4 External financial control – documentation
WP7.2 Accreditation documentation
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (3 persons x 4 days: Milan Gocic, Slavisa Trajkovic, Borislava Blagojevic); WP7.3 UNIME (2 persons x 7 days)
  Students: WP4.3 Implementation of students’ internships UNSA (10 persons x 12 days -> 10 + 2); WP7.3 MUHEC (2 persons x 14 days -> 12 + 2: Tamara Nikolić, Aleksa Dugonjivac)
SMS students: BOKU (2 x 5 months: Borko Radivojević), UNIME (2 x 5 months: Žarko Radivojević), UNSA (2 x 5 months: Ana Stojanović, Andrea Jakić)
WP4.4 Implementation of Master curricula and reporting
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 7: P2 - BOKU
Staff costs (SC-032-036) – documentation
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (3 persons x 4 days: Kurt Glock, Daniel Wildt, Angelika Riegler)
SMS:
  Staff: UNI (1 person x 7 days: Michael Tritthart), UNSA (3 persons x 7 days: Markus Peter, Peter Flodl, Christian Scheidl)
  Students: UNI (1 person x 2 months: Ana Maria Madrigal Sanchez)
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 8: P3 - MUHEC
Staff costs – documentation
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (3 persons x 4 days: Sally Priest, Simon McCarthy, Giuseppina Joyce)
SMS:
  Staff: UNI (3 persons x 7 days: Baljit Binning)
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 9: P4 - KPU
Staff costs – documentation
WP7.2 Accreditation documentation
Printing materials – Subcontracing
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (2 persons x 4 days: Saša Mijalković, Nikola Stanisavljević)
  Students: WP7.3 OE (2 persons x 14 days -> 12 + 2)
SMS:
  Staff: MUHEC (1 person x 7 days)
  Students: OE (3 persons x 5 months); UBL (2 persons x 5 months)
WP4.4 Implementation of Master curricula and reporting
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 10: P5 - UPKM
Staff costs – documentation
WP7.2 Accreditation documentation
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (3 persons x 4 days: Nebojša Arsić, Aleksandra Petrović, Ljiljana Murganić)
  Students: WP4.3 Implementation of students’ internships UNI (5 persons x 12 days -> 10 + 2); WP7.3 TUC (1 person x 14 days -> 12 + 2)
SMS:
  Staff: OE (1 person x 7 days)
  Students: UNSA (7 persons x 2 months)
WP4.4 Implementation of Master curricula and reporting
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 11: P6 - UNSA
Staff costs – documentation (P6-SC-047 TS and contract, SC-030 and SC-037 address)
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in London (3 persons x 4 days: Emina Hadžić, Ammar Šarić, Suvada Jusić); WP7.3 UNIME (4 persons x 7 days: Emina Hadžić, Hata Milišić, Nina Dragičević)
  Students: WP4.3 Implementation of students’ internships UNI (5 persons x 12 days -> 10 + 2)
SMS:
  Staff: UNI (1 person x 7 days: Emina Hadžić), UNIME (3 persons x 7 days: Emina Hadžić, Sanjin Albinović), UNIME (2 persons x 14 days: Ammar Šarić, Naida Ademović)
  Students: UNI (2 persons x 5 months: Nejra Muhedin, Šemsa Imširović); BOKU (2 persons x 5 months: Merima Trako, Selena Grizić); UNIME (3 persons x 2 months: Amar Šurković, Selma Čolo)
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 12: P7 - UBL
Staff costs – documentation + TS-020 signed
Printing - subcontracting
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (2 persons x 4 days: Radoslav Ivaniš, Milan Stanivuković); WP7.3 OE (2 persons x 7 days: Velibor Lalić, Predrag Ćeranić)
  Students: WP4.3 Implementation of students’ internships KPU (2 persons x 12 days -> 10 + 2); WP7.3 OE (1 person x 14 days -> 12 + 2: Radoslav Ivaniš)
SMS:
  Students: KPU (2 persons x 5 months); OE (1 person x 2 months)
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 13: P8 - TCASU
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (1 person x 4 days: Predrag Stanojevic)
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 14: P9 - UNIME
Staff costs – documentation
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (3 persons x 4 days: Giuseppe Tito Aronica, Francesca Pollicino, Brunella Bonaccorso)
SMS:
  Staff: UNI (5 persons x 7 days), UNSA (3 persons x 7 days: Brunella Bonaccorso)
  Students: UNI (1 person x 5 months), UNSA (2 persons x 5 months)
Amendment to the UNIME-UNI inter-institutional agreement
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 15: P10 - OE
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (2 persons x 4 days: Ancza Erzsébet, Farkas Gabriella)
SMS:
  Staff: UNI (1 person x 7 days)
  Students: KPU (1 x 2 months: Éva Beke)
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 16: P11 - UNID
Staff costs – documentation
WP7.2 Accreditation documentation
Printing materials - Subcontracing
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (2 persons x 4 days: Radovan Karkalić, Sasa Stojanovic)
  Students: WP4.3 Implementation of students’ internships UNI (5 persons x 12 days -> 10 + 2)
WP4.4 Implementation of Master curricula and reporting
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 17: P12 - TUC
Staff costs – documentation
Travel Costs & Costs of Stay:
  Staff: WP8.2 Meeting in Sarajevo (2 persons x 4 days: Georgios Stavroulakis, Georgios Tairidis)
SMS:
  Staff: UNI (3 persons x 7 days), UNSA (3 persons x 7 days)
  Students: UNSA (1 person x 2 months)
WP8.5 Final report
Development of master curricula for natural disasters risk management in Western Balkan countries

## Slide 18: 10 % of HEI’s financing
Development of master curricula for natural disasters risk management in Western Balkan countries